CORDOVA PUBLIC COLLEGE

College of Computer Studies

Gabi, Cordova, Cebu, Philippines

Software Project Management Plan

For

Herbal AI: A Digital Repository of Philippine Herbal Medicine with AI-Assisted Preparation

By:

Kevin C. Mercado  - Project Manager

Devon Descipulo  -  Backend Developer

Eumar Cabaluna - Frontend Developer

Submitted in partial fulfillment of the requirements for the

Degree of Bachelor of Science in Information Technology (BSIT)

May 26, 2026

# Signature

This Software Project Management Plan has been reviewed and is hereby approved for submission to the Capstone Evaluation Panel of the College of Computer Studies, Cordova Public College.

| Project Manager | Kevin C. Mercado Name / Signature / Date |
| --- | --- |
| Backend Developer | Devon Descipulo Name / Signature / Date |
| Frontend Developer | Eumar Cabaluna Name / Signature / Date |
| Adviser | Mr. Nickasio P. Amoin Jr. Name / Signature / Date |
| Panel Member | Name / Signature / Date |
| Panel Member | Name / Signature / Date |

# Change History

The following table records all revisions made to this Software Project Management Plan document.

| Version | Date | Description of Changes | Author |
| --- | --- | --- | --- |
| 1.0 | May 26, 2026 | Initial SPMP document creation following IEEE Std 1058-1998 format as prescribed by Cordova Public College CCS capstone documentation guidelines. | Capstone Development Team |
| 2.0 | July 8, 2026 | Revised to reflect the current Advanced Integrated Prototype (v2.5) status. Updated project phase to “Integration, Stabilization, Testing, and Deployment Preparation,” revised milestones, schedule, risk register, and quality assurance plan to match actual progress. Removed Annex A (Agile Sprint Backlog Template) and Annex C (Definition of Done); merged relevant Definition of Done criteria into the Quality Control Plan; added the Capstone Documentation and Artifacts List. | Kevin C. Mercado |

# Preface

This Software Project Management Plan (SPMP) defines the framework for managing the development of Herbal AI: A Digital Repository of Philippine Herbal Medicine with AI-Assisted Preparation. It is prepared by the three-person capstone development team of the College of Computer Studies, Cordova Public College, following the IEEE Std 1058-1998 standard for Software Project Management Plans.

This document covers the project overview, schedule, team roles, risk management, technical processes, and quality assurance plan for the 4-month development lifecycle of the Herbal AI web application.

# Table of Contents

Contents

Signature	2

Change History	3

Preface	4

Table of Contents	5

List of Figures	8

List of Tables	9

1.   Overview	10

1.1.   Project Summary	10

1.1.1  Purpose, Scope and Objectives	10

1.1.2  Assumptions and Constraints	10

1.1.3  Project Deliverables	11

1.1.4  Schedule and Budget Summary	12

1.2.   Evolution of Plan	13

2.   References	14

3.   Definitions	15

4.   Project Organization	16

4.1.   External Interface	16

4.2.   Internal Structure	16

4.3.   Roles and Responsibilities	16

5.   Managerial Process Plans	18

5.1.   Start-up Plan	18

5.1.1  Estimation Plan	18

5.1.2  Staffing Plan	18

5.1.3  Resource Acquisition Plan	18

5.1.4  Project Staff Training Plan	19

5.2.   Work Plan	20

5.2.1  Work Activities	20

5.2.2  Schedule Allocation	22

5.2.3  Resource Allocation	23

5.2.4  Budget Allocation	24

5.3.   Control Plan	25

5.3.1  Requirements Control Plan	25

5.3.2  Schedule Control Plan	25

5.3.3  Budget Control Plan	25

5.3.4  Quality Control Plan	25

5.3.5  Reporting Plan	26

5.3.6  Metrics Collection Plan	26

5.3.7  Risk Management Plan	26

5.3.8  Project Closeout Plan	28

6.   Technical Process Plans	29

6.1.   Process Model	29

6.2.   Methods, Tools, and Techniques	29

6.3.   Infrastructure Plan	30

6.4.   Product Acceptance Plan	31

7.   Supporting Process Plans	32

7.1.   Configuration Management Plan	32

7.2.   Verification and Validation Plan	32

7.3.   Documentation Plan	37

7.4.   Quality Assurance Plan	37

7.5.   Reviews and Audits	38

7.6.   Problem Resolution Plan	38

7.7.   Process Improvement Plan	38

8.   Additional Plans	40

9.   Annexes	41

9.1.   Capstone Documentation and Artifacts List	41

The following table lists the complete set of documents and artifacts required for the Herbal AI capstone project, along with their current status as of this revision. This list is consistent with the equivalent list provided in the companion SRS document.	41

Table 14 – Capstone Documentation and Artifacts List	41

Annex A – Team Communication Channels	42

5.3.5  Reporting Plan

5.3.6  Metrics Collection Plan

5.3.7  Risk Management Plan

5.3.8  Project Closeout Plan

6.  Technical Process Plans

6.1.  Process Model

6.2.  Methods, Tools, and Techniques

6.3.  Infrastructure Plan

6.4.  Product Acceptance Plan

7.  Supporting Process Plans

7.1.  Configuration Management Plan

7.2.  Verification and Validation Plan

7.3.  Documentation Plan

7.4.  Quality Assurance Plan

7.5.  Reviews and Audits

7.6.  Problem Resolution Plan

7.7.  Process Improvement Plan

8.  Additional Plans

9.  Annexes

# List of Figures

Figure 1 – Agile Sprint Cycle for Herbal AI Development (Section 6.1)

Figure 2 – Project Organization Chart (Section 4.2)

# List of Tables

Table 1 – Document Change History

Table 2 – Project Deliverables

Table 3 – Project Schedule Summary (Week-by-Week)

Table 4 – Roles and Responsibilities

Table 5 – Staffing Plan

Table 6 – Resource Acquisition Plan

Table 7 – Work Activities and Work Breakdown Structure

Table 8 – Resource Allocation

Table 9 – Budget Allocation

Table 10 – Risk Management Plan

Table 11 – Methods, Tools, and Techniques

Table 12 – Verification and Validation Test Plan

Table 13 – Documentation Plan

Table 14 – Capstone Documentation and Artifacts List

# 1.   Overview

## 1.1.   Project Summary

### 1.1.1  Purpose, Scope and Objectives

Herbal AI is a web-based digital repository for Philippine herbal medicine designed to transform passive reading into active, safe guidance. The system addresses the critical lack of a centralized, verified, and accessible platform for Philippine traditional botanical knowledge by providing:

- A verified digital herb library with DOH-grounded information

- An AI-powered chat assistant (Dr. Ai) for safe preparation and dosage guidance

- A crowdsourced herb suggestion system with admin verification

- A community forum and private messaging system for knowledge sharing

- An admin dashboard for full content and user management

The project is being developed as a capstone requirement for the Bachelor of Science in Information Technology (BSIT) program at the College of Computer Studies, Cordova Public College. The system is aligned with Republic Act No. 8423 (Traditional and Alternative Medicine Act of 1997) and DOH-verified herbal medicine guidelines.

As of this revision, the project has progressed into an Advanced Integrated Prototype (v2.5) and entered the Integration, Stabilization, Testing, and Deployment Preparation phase. Relative to the original schedule baseline, the team is ahead of schedule. Measured against the full SRS/SPMP final scope, the system is approximately 75% feature-complete; measured against defense-ready, fully tested, and deployed quality, the system is approximately 60–65% complete. Remaining work is concentrated on automated testing, frontend lint cleanup, deployment verification, and final documentation.

The scope of this SPMP covers the complete 4-month development lifecycle — from initial planning and design through implementation, testing, and final delivery — of the Herbal AI web application.

### 1.1.2  Assumptions and Constraints

The following assumptions and constraints apply to this project:

Assumptions:

- All three team members will be available for the full 4-month development period.

- Internet connectivity will be consistently available for development, API access, and cloud database connections.

- Google Gemini API will remain available and accessible throughout the project.

- PostgreSQL cloud hosting (free tier) will be sufficient for development and testing phases.

- The capstone adviser will provide timely feedback within one week of document or prototype submission.

Constraints:

- The team consists of only 3 members with limited professional coding experience — all are student developers.

- No dedicated project budget is allocated; all tools and services must use free-tier or open-source options.

- The system must be completed and ready for final defense within 4 months (approximately 16 weeks).

- The Gemini API key must remain secured as a backend environment variable at all times.

- The Community Forum and Private Messaging features are included in scope but are lower priority than the core Herb Library and Dr. Ai features.

### 1.1.3  Project Deliverables

Table 2 – Project Deliverables

| Deliverable | Description | Due Date | Recipient | Status |
| --- | --- | --- | --- | --- |
| Software Requirements Specification (SRS) | Complete IEEE 830-1998 compliant SRS document | Month 1, Week 2 | Capstone Adviser | Complete |
| Software Project Management Plan (SPMP) | Complete IEEE 1058-1998 compliant SPMP document | Month 1, Week 2 | Capstone Adviser | Complete |
| System Design Document | Database schema, architecture diagrams, UI wireframes | Month 1, Week 4 | Capstone Adviser | In progress |
| Working Prototype v1.0 | Core features: Herb Library, Search, Sign In/Sign Up | Month 2, Week 4 | Capstone Adviser | Complete |
| Working Prototype v2.0 | Dr. Ai Chat, Herb Suggestion, Admin Dashboard | Month 3, Week 3 | Capstone Adviser | Complete |
| Working Prototype v3.0 | Community Forum, Private Messaging, full system | Month 4, Week 2 | Capstone Panel | Implemented — corresponds to the current Advanced Integrated Prototype (v2.5); pending full verification |
| Final System (v1.0 Release) | Fully tested and deployed Herbal AI web application | Month 4, Week 4 | Capstone Panel | Pending — testing and deployment in progress |
| Final Defense Presentation | Capstone defense slides and live system demonstration | Month 4, Week 4 | Capstone Panel | Pending |

### 1.1.4  Schedule and Budget Summary

The Herbal AI project spans 4 months (approximately 16 weeks) from June 2026 to September 2026. The project follows an Agile development approach with 2-week sprint cycles.

Table 3 – Project Schedule Summary (Week-by-Week)

| Month | Week | Major Activities | Milestone |
| --- | --- | --- | --- |
| Month 1 (June 2026) | Week 1 | Project planning, SRS finalization, SPMP creation, team role assignment | SRS & SPMP submitted to adviser |
|  | Week 2 | Database schema design, ERD, class diagram, UI wireframes in Figma | Design documents approved |
|  | Week 3 | Project environment setup, Next.js frontend scaffold, Express.js backend scaffold | Development environment ready |
|  | Week 4 | User authentication (Sign In, Sign Up, JWT), PostgreSQL schema setup | Auth system working |
| Month 2 (July 2026) | Week 5 | Herb Library backend API (GET /api/herbs, GET /api/herbs/:id) | Herb API endpoints live |
|  | Week 6 | Herb Library frontend (library page, herb cards, search, category filter) | Herb Library page working |
|  | Week 7 | Herb Detail page (preparation steps, dosage, warnings, images) | Herb Detail page working |
|  | Week 8 | Google OAuth SSO integration, user profile page — Prototype v1.0 review | Prototype v1.0 demo to adviser |
| Month 3 (August 2026) | Week 9 | Dr. Ai chat backend — Gemini API integration, system instruction prompts | Dr. Ai responding correctly |
|  | Week 10 | Dr. Ai chat frontend — streaming UI, quick prompts, safety disclaimers | Dr. Ai frontend complete |
|  | Week 11 | Herb Suggestion system (contributor form, image upload, Pending queue) | Suggestion system working |
|  | Week 12 | Admin Dashboard (pending review, approve/reject, herb catalog management) — Prototype v2.0 | Prototype v2.0 demo to adviser |
| Month 4 (September 2026) | Week 13 | Community Forum backend and frontend (threads, replies, tags) | Forum feature working |
|  | Week 14 | Private Messenger backend and frontend (DMs, read/unread status) — Prototype v3.0 | Prototype v3.0 demo to adviser |
|  | Week 15 | Full system integration testing, bug fixing, performance optimization, UI polish | All bugs resolved |
|  | Week 16 | Final deployment, documentation finalization, defense preparation | System deployed & defense ready |

Actual Progress Note (as of this revision, July 2026): The team is currently ahead of this original baseline. Weeks 1–12 (Months 1–3) are complete as planned, including authentication, the Herb Library, Dr. Ai, the Herb Suggestion System, and the Admin Verification Dashboard. Weeks 13–14 (Community Forum and Private Messaging) are also complete, ahead of their Month 4 target, though pending full verification. The remaining weeks (15–16) have been re-scoped from general “testing & deployment” to the specific remaining tasks: automated testing, frontend lint cleanup, deployment verification, and final documentation — see Table 7 (Work Activities) and Section 5.2.2 for current status.

Budget Summary: The project operates on a zero-cost budget utilizing exclusively free-tier and open-source tools. No financial expenditure is required for software licenses or paid hosting during the development phase. Any minimal costs (domain registration, premium hosting for final deployment) will be covered personally by team members if needed.

## 1.2.   Evolution of Plan

This SPMP is a living document and will be updated as the project progresses. Scheduled updates will occur:

- At the start of each month (monthly review of schedule, risks, and resource allocation)

- When significant scope changes are approved by the capstone adviser

- When major risks are identified that affect the project schedule or deliverables

- After each prototype demonstration to incorporate adviser feedback

All updates to this SPMP will be recorded in the Change History table. The project manager (Kevin C. Mercado) is responsible for maintaining and distributing updated versions of this plan to the capstone adviser and all team members.

# 2.   References

1.  IEEE Std 1058-1998 – IEEE Standard for Software Project Management Plans. IEEE Computer Society.

2.  IEEE Std 830-1998 – IEEE Recommended Practice for Software Requirements Specifications. IEEE Computer Society.

3.  Republic Act No. 8423 – Traditional and Alternative Medicine Act of 1997. Philippine DOH, Manila.

4.  DOH Clinical Guidelines on 10 Scientifically Validated Philippine Medicinal Plants. Department of Health, Philippines.

5.  Next.js Official Documentation. Vercel, Inc., 2026. https://nextjs.org/docs

6.  Express.js Official Documentation. Node.js Foundation. https://expressjs.com/

7.  PostgreSQL Documentation. PostgreSQL Global Development Group. https://www.postgresql.org/docs/

8.  Google Gemini API Technical Reference. Google DeepMind, 2026. https://ai.google.dev/

9.  Herbal AI Software Requirements Specification (SRS) v1.0. Capstone Development Team, May 2026.

# 3.   Definitions

The following terms and acronyms are used throughout this SPMP:

| Term / Acronym | Definition |
| --- | --- |
| SPMP | Software Project Management Plan — this document. |
| SRS | Software Requirements Specification — the companion requirements document for Herbal AI. |
| Agile | An iterative software development methodology focused on short sprint cycles, continuous feedback, and adaptive planning. |
| Sprint | A fixed 2-week development period in Agile methodology during which specific features are planned, developed, and reviewed. |
| WBS | Work Breakdown Structure — a hierarchical decomposition of project work activities. |
| Milestone | A significant checkpoint in the project schedule that marks the completion of a major deliverable or phase. |
| Dr. Ai | The AI-powered chat assistant module of Herbal AI, powered by the Google Gemini API. |
| JWT | JSON Web Token — used for secure user authentication and session management. |
| DOH | Department of Health, Philippines — the regulatory body for Philippine medicinal plant standards. |
| RA 8423 | Republic Act No. 8423 — Traditional and Alternative Medicine Act of 1997. |
| BSIT | Bachelor of Science in Information Technology — the degree program under which this capstone is submitted. |
| CCS | College of Computer Studies, Cordova Public College. |
| PM | Project Manager — Kevin C. Mercado, responsible for planning, coordination, and documentation. |
| QA | Quality Assurance — processes ensuring the system meets all specified requirements and quality standards. |
| V&V | Verification and Validation — testing processes confirming the system is built correctly and meets user needs. |

# 4.   Project Organization

## 4.1.   External Interface

The Herbal AI project interfaces with the following external organizational entities:

- Cordova Public College (CPC) – College of Computer Studies: The parent institution overseeing the capstone project. The CCS Dean and faculty provide the academic framework, documentation standards, and defense panel.

- Capstone Adviser: The assigned faculty adviser who reviews all deliverables, provides technical and academic feedback, and approves project progression at each milestone.

- Capstone Defense Panel: The evaluation committee composed of CCS faculty members who conduct the final defense and evaluate the completeness, quality, and academic merit of the Herbal AI system.

- Google (Gemini API): External service provider for the AI assistant engine. The project depends on Google's Gemini API availability and terms of service.

- End Users: Filipino general public, herbal medicine enthusiasts, researchers, and contributors who will use the Herbal AI platform.

## 4.2.   Internal Structure

The Herbal AI development team consists of three student developers organized as follows:

| Position | Name | Primary Responsibility |
| --- | --- | --- |
| Project Manager | Kevin C. Mercado | Overall project coordination, documentation (SRS, SPMP), stakeholder communication, sprint planning, system architecture design |
| Backend Developer | Devon Descipulo | Express.js REST API, PostgreSQL database management, JWT authentication, Gemini API integration, server security |
| Frontend Developer | Eumar Cabaluna | Next.js UI/UX implementation, Tailwind CSS responsive design, frontend-backend API integration, accessibility |

Due to the small team size, all members are expected to cross-collaborate and assist each other during high-workload periods. Kevin C. Mercado serves as the primary point of contact with the capstone adviser.

## 4.3.   Roles and Responsibilities

Table 4 – Roles and Responsibilities

| Work Activity | Kevin C. Mercado (Project Manager) | Devon Descipulo (Backend Dev) | Eumar Cabaluna (Frontend Dev) |
| --- | --- | --- | --- |
| Project Planning & Documentation | Lead | Support | Support |
| Database Design (PostgreSQL Schema) | Review | Lead | Support |
| Backend API Development (Express.js) | Review | Lead | — |
| Frontend UI Development (Next.js) | Review | — | Lead |
| Authentication (JWT + Google SSO) | Review | Lead | Support |
| Gemini API Integration (Dr. Ai) | Review | Lead | Support |
| Admin Dashboard Development | Review | Support | Lead |
| Herb Suggestion System | Review | Lead | Lead |
| Community Forum & Messaging | Review | Lead | Lead |
| Testing & Quality Assurance | Lead | Support | Support |
| Deployment & Go-Live | Lead | Lead | Support |
| Defense Presentation | Lead | Support | Support |

# 5.   Managerial Process Plans

## 5.1.   Start-up Plan

### 5.1.1  Estimation Plan

The project effort, schedule, and resources were estimated using the following methods:

- Analogy-based Estimation: Estimated development time based on comparable capstone web application projects completed by previous CCS students.

- Expert Judgment: Team members assessed their individual skill levels and estimated time needed per feature based on their familiarity with Next.js, Express.js, and PostgreSQL.

- Bottom-up Estimation: Each feature was broken down into tasks and individually estimated, then aggregated to form the total project schedule.

Key estimation parameters:

- Total project duration: 16 weeks (4 months)

- Sprint length: 2 weeks per sprint (8 sprints total)

- Average working hours per week per member: 15–20 hours

- Total estimated effort: approximately 720–960 person-hours across all 3 members

- Re-estimation will be performed at the start of each month based on actual progress

### 5.1.2  Staffing Plan

Table 5 – Staffing Plan

| Role | Name | Month 1 | Month 2 | Month 3 | Month 4 | Total Hours |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | Kevin C. Mercado | 20 hrs/wk | 15 hrs/wk | 15 hrs/wk | 20 hrs/wk | ~280 hrs |
| Backend Developer | Devon Descipulo | 15 hrs/wk | 20 hrs/wk | 20 hrs/wk | 15 hrs/wk | ~280 hrs |
| Frontend Developer | Eumar Cabaluna | 15 hrs/wk | 20 hrs/wk | 20 hrs/wk | 15 hrs/wk | ~280 hrs |

### 5.1.3  Resource Acquisition Plan

Table 6 – Resource Acquisition Plan

| Resource | Type | Source | Cost | Required By |
| --- | --- | --- | --- | --- |
| Next.js Framework | Software | Open-source (npmjs.com) | Free | Month 1, Week 3 |
| Express.js Framework | Software | Open-source (npmjs.com) | Free | Month 1, Week 3 |
| PostgreSQL Database | Software/Cloud | Neon DB (free tier) — Development | Free | Month 1, Week 3 |
| Google Gemini API | External API | Google AI Studio (free tier) | Free | Month 3, Week 1 |
| GitHub Repository | Version Control | GitHub (free plan) | Free | Month 1, Week 1 |
| Docker | Containerization | Open-source (Docker Hub) | Free | Month 3, Week 2 |
| GitHub Actions | CI/CD Pipeline | GitHub (included in free plan) | Free | Month 3, Week 2 |
| Hostinger VPS | Cloud Hosting (Backend + Database) | Hostinger (KVM 1 — Entry-level VPS, $4.99/month) | ~₱300 – 400/month | Month 4, Week 1 |
| Hostinger Domain | Domain Registration | Hostinger (.com or .ph) | ₱500 – 1,200/year | Month 4, Week 1 |
| Figma | Design Tool | Figma (free plan) | Free | Month 1, Week 2 |
| VS Code | IDE | Open-source (Microsoft) | Free | Month 1, Week 1 |
| Postman | API Testing | Postman (free tier) | Free | Month 2, Week 1 |
| Personal Laptops (x3) | Hardware | Owned by team members | Free | Month 1, Week 1 |

### 5.1.4  Project Staff Training Plan

The following training activities are planned to ensure all team members have the necessary skills to successfully complete the Herbal AI project:

| Training Topic | Who | Method | Timing |
| --- | --- | --- | --- |
| Next.js fundamentals (App Router, SSR, API routes) | Eumar Cabaluna | Online tutorials (official Next.js docs, YouTube) | Month 1, Week 1-2 |
| Express.js REST API design and middleware | Devon Descipulo | Online tutorials, official Express.js docs | Month 1, Week 1-2 |
| PostgreSQL schema design and SQL queries | Devon Descipulo | Online tutorials, PostgreSQL documentation | Month 1, Week 2 |
| JWT authentication implementation | Devon Descipulo | Online tutorials and sample projects | Month 1, Week 3 |
| Google Gemini API integration | Devon Descipulo | Google AI Studio documentation | Month 2, Week 4 |
| Tailwind CSS responsive design | Eumar Cabaluna | Tailwind CSS official documentation | Month 1, Week 1 |
| Git and GitHub version control workflow | All members | Team peer training session | Month 1, Week 1 |
| Agile/Scrum sprint methodology | All members (led by PM) | Team orientation session | Month 1, Week 1 |

## 5.2.   Work Plan

### 5.2.1  Work Activities

The work breakdown structure (WBS) for the Herbal AI project is organized into the following major work activities:

Table 7 – Work Activities and Work Breakdown Structure

| WBS ID | Work Activity | Sub-Activities | Owner | Duration | Status |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Project Planning & Documentation | SRS, SPMP, system design, ERD, class diagram, use case diagram | PM | Month 1 | Completed |
| 2.0 | Development Environment Setup | GitHub repo, project scaffold, database setup, environment variables | All | Week 3 | Completed |
| 3.0 | User Authentication System | Sign Up, Sign In, JWT, Google SSO, role-based access control | Backend | Week 4 | Completed — includes refresh token, email verification, forgot/reset password, and Google OAuth SSO |
| 4.0 | Herb Library Module | Herb API endpoints, library page, search, filter, herb cards, DOH status | All | Weeks 5-6 | Completed |
| 5.0 | Herb Detail Page | Full herb info display, preparation steps, dosage, warnings, image | Frontend | Week 7 | Completed |
| 6.0 | Dr. Ai Chat Assistant | Gemini API integration, chat UI, quick prompts, safety disclaimer, streaming | All | Weeks 9-10 | Completed — includes RAG/knowledge-base support |
| 7.0 | Herb Suggestion System | Suggestion form, image upload, Pending queue, contributor notifications | All | Week 11 | Completed; status-change notifications pending |
| 8.0 | Admin Dashboard | Pending review panel, approve/reject, herb catalog management, user management | All | Week 12 | Completed — renamed Admin Verification Dashboard; includes user management and system stats; audit logging pending |
| 9.0 | Community Forum | Thread creation, replies, tags, likes, pinning, moderation | All | Week 13 | Implemented; pending full verification |
| 10.0 | Private Messenger | DM system, chat history, read/unread, notifications | All | Week 14 | Implemented; pending full verification (renamed Private Messaging) |
| 11.0 | Testing & QA | Unit testing, integration testing, UAT, performance testing, bug fixing | PM + All | Weeks 15-16 | In progress — automated tests and frontend lint cleanup pending |
| 12.0 | Deployment & Delivery | Cloud deployment, final documentation, defense presentation | PM + Backend | Week 16 | Pending |

### 5.2.2  Schedule Allocation

The project schedule follows a 2-week Agile sprint cycle. Each sprint includes: Sprint Planning (Day 1), Development (Days 2-12), Sprint Review with Adviser (Day 13-14), and Retrospective (Day 14).

| Sprint | Weeks | Features Developed | Review Milestone | Status |
| --- | --- | --- | --- | --- |
| Sprint 1 | Weeks 1-2 | Project planning, SRS, SPMP, system design, ERD, Figma wireframes | Documents submitted to adviser | Completed |
| Sprint 2 | Weeks 3-4 | Dev environment setup, Next.js + Express.js scaffold, PostgreSQL schema, Sign In/Sign Up with JWT | Auth system working demo | Completed |
| Sprint 3 | Weeks 5-6 | Herb Library API endpoints, Library page, search, category filters, herb cards | Herb Library browsable | Completed |
| Sprint 4 | Weeks 7-8 | Herb Detail page, Google SSO, user profile, Prototype v1.0 preparation | Prototype v1.0 demo to adviser | Completed |
| Sprint 5 | Weeks 9-10 | Dr. Ai Gemini API integration, chat backend, chat frontend, quick prompts, safety disclaimer | Dr. Ai responding correctly | Completed |
| Sprint 6 | Weeks 11-12 | Herb Suggestion form, image upload, Admin Dashboard, Prototype v2.0 preparation | Prototype v2.0 demo to adviser | Completed |
| Sprint 7 | Weeks 13-14 | Community Forum (threads, replies, tags), Private Messenger (DMs), Prototype v3.0 | Prototype v3.0 demo to adviser | Implemented; pending full verification |
| Sprint 8 | Weeks 15-16 | Automated test suite, frontend lint cleanup, integration/regression testing, deployment verification, documentation finalization, defense preparation | System stabilized and defense-ready | In progress |

Figure 1 – Herbal AI Project Gantt Chart

The Gantt chart above shows all 8 Agile sprints across the 4-month development schedule. Diamond shapes represent major milestones (Prototype v1.0, v2.0 demos, the current Advanced Integrated Prototype v2.5, and Final Defense). As of this revision, Sprints 1–7 are complete (Sprint 7 pending full verification), and Sprint 8 is in progress, re-scoped to focus on automated testing, frontend lint cleanup, deployment verification, and final documentation.

### 5.2.3  Resource Allocation

Table 8 – Resource Allocation

| Work Activity | Kevin C. Mercado | Devon Descipulo | Eumar Cabaluna | Tools |
| --- | --- | --- | --- | --- |
| Planning & Docs | 80% | 10% | 10% | Google Docs, Figma |
| Auth System | 10% | 70% | 20% | Express.js, PostgreSQL, JWT |
| Herb Library | 10% | 50% | 40% | Express.js, Next.js, PostgreSQL |
| Herb Detail Page | 10% | 20% | 70% | Next.js, Tailwind CSS |
| Dr. Ai Module | 10% | 60% | 30% | Gemini API, Express.js, Next.js |
| Herb Suggestion | 10% | 50% | 40% | Express.js, Next.js, PostgreSQL |
| Admin Dashboard | 10% | 30% | 60% | Next.js, Tailwind CSS |
| Forum & Messenger | 10% | 50% | 40% | Express.js, Next.js, PostgreSQL |
| Testing & QA | 50% | 25% | 25% | Postman, browser DevTools |
| Deployment | 30% | 50% | 20% | Vercel, Railway/Render |

### 5.2.4  Budget Allocation

Table 9 – Budget Allocation

| Resource | Estimated Cost | Notes |
| --- | --- | --- |
| Software Tools (Next.js, Express.js, PostgreSQL, Tailwind CSS) | PHP 0.00 | All open-source and free |
| Cloud Services (Neon DB free tier for development) | PHP 0.00 | Free-tier sufficient for development phase |
| Docker & GitHub Actions | PHP 0.00 | Open-source CI/CD tools |
| Google Gemini API | PHP 0.00 | Free-tier quota sufficient for development and testing |
| GitHub Repository | PHP 0.00 | Free public/private repositories |
| Figma Design Tool | PHP 0.00 | Free plan for up to 3 editors |
| Hostinger VPS (KVM 1 — Entry-level, $4.99/month) | ~PHP 300 – 400/month | Cheapest VPS plan. Runs backend (Express.js), PostgreSQL, and Docker containers. 1-2 months rental for final deployment and defense (Month 4). Includes root access, NVMe storage, and weekly backups. |
| Hostinger Domain (.com or .ph) | PHP 500 – 1,200/year | Domain registration for public access during defense and final deployment. |
| Printing (documents for defense) | PHP 300 – 600 | SRS, SPMP, and supporting documents printed |
| TOTAL ESTIMATED BUDGET | PHP 1,700 – 3,000 | Minimal cost. Cheapest Hostinger VPS + domain + printing for defense documents. |

## 5.3.   Control Plan

### 5.3.1  Requirements Control Plan

All changes to the Herbal AI system requirements must go through the following process:

1.  Any team member or adviser identifies a requirement change.

2.  The change is discussed in the next sprint planning meeting.

3.  If approved by the project manager and adviser, the SRS is updated accordingly.

4.  The Change History table in the SRS is updated with the version number, date, and description.

5.  All team members are notified of the change via the team group chat (Messenger/Discord).

### 5.3.2  Schedule Control Plan

Schedule progress is monitored using the following mechanisms:

- Weekly check-ins every Friday — each member reports completed tasks and blockers.

- Sprint review at the end of each 2-week sprint — completed features are demonstrated.

- If a sprint deliverable is delayed by more than 3 days, the project manager will assess whether to adjust the schedule or reallocate tasks.

- The week-by-week schedule table (Table 3) serves as the baseline for measuring actual vs. planned progress.

### 5.3.3  Budget Control Plan

Since the project operates on a zero-cost budget, budget control primarily involves monitoring free-tier API usage limits:

- Google Gemini API usage will be monitored monthly to ensure it stays within the free-tier quota.

- Neon DB storage will be monitored to ensure it stays within the free-tier limit.

- Vercel deployment bandwidth will be monitored monthly.

- Any unexpected costs will be discussed in the team and reported to the adviser before incurring expenses.

### 5.3.4  Quality Control Plan

Quality control for Herbal AI will be implemented through:

- Code reviews — each feature branch is reviewed by at least one other team member before merging to main.

- Functional testing — all features are manually tested against the functional requirements in the SRS before marking as complete.

- Regression testing — after each sprint, all previously completed features are re-tested to ensure new changes did not break existing functionality.

- Adviser review — prototypes are demonstrated to the capstone adviser at the end of each month for external quality feedback.

- Definition of Done: A feature is considered “done” only when it is fully implemented as described in the SRS, passes its related test cases in the V&V Test Plan (Table 12), has been reviewed and approved by at least one other team member, has been merged to the main branch, and is demonstrable in the working prototype without errors. Under this definition, the Community Forum and Private Messaging modules are implemented but not yet formally “done,” pending full verification.

### 5.3.5  Reporting Plan

The following reporting mechanisms are used throughout the project:

| Report Type | Frequency | Prepared By | Recipients |
| --- | --- | --- | --- |
| Sprint Progress Report | Every 2 weeks (end of sprint) | Project Manager | Team members, Capstone Adviser |
| Weekly Team Check-in | Every Friday | All members (verbal/chat) | Team members only |
| Monthly Status Update | End of each month | Project Manager | Capstone Adviser |
| Prototype Demo | End of Months 2, 3, 4 | All team members | Capstone Adviser, Panel |
| Risk Status Update | Monthly or when risk arises | Project Manager | Team members, Capstone Adviser |

### 5.3.6  Metrics Collection Plan

The following metrics will be collected and tracked throughout the project:

- Sprint velocity — number of features/tasks completed per sprint vs. planned.

- Bug count — number of bugs found and resolved per sprint.

- Test pass rate — percentage of test cases passing at each sprint review.

- API response time — measured during testing to ensure performance targets are met.

- Page load time — measured using browser DevTools to ensure pages load within 3 seconds.

### 5.3.7  Risk Management Plan

Table 10 – Risk Management Plan

| Risk ID | Risk Description | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-01 | Team member unavailable due to academic workload or personal reasons | Medium | High | Cross-train all members on each other's tasks. Maintain shared documentation so any member can continue another's work. |
| R-02 | Google Gemini API rate limit exceeded during development or testing | Medium | Medium | Monitor API usage regularly. Use mock responses during development. Upgrade plan if needed for final testing. |
| R-03 | Gemini API becomes unavailable or terms change | Low | High | Design Dr. Ai module with an abstraction layer so a different AI API (e.g., OpenAI) can be swapped in if needed. |
| R-04 | PostgreSQL cloud database (free tier) storage limit exceeded | Low | Medium | Keep database lean during development. Use seed data only. Upgrade to paid tier only for final deployment if needed. |
| R-05 | No automated test suite currently exists, increasing the risk of undetected regressions | High | High | Prioritize introducing unit and integration tests in Sprint 8. Until automated coverage exists, rely on structured manual regression testing against the V&V Test Plan (Table 12) before each merge. |
| R-06 | Frontend lint errors remain unresolved | Medium | Medium | Allocate dedicated time in Sprint 8 for the frontend developer to resolve outstanding ESLint errors before defense; treat lint cleanup as a defense-readiness blocker. |
| R-07 | Adviser feedback requires significant system changes | Medium | High | Submit deliverables early. Maintain buffer weeks in the schedule. Communicate scope constraints to adviser proactively. |
| R-08 | Data privacy and security concerns (user data, password storage, API key exposure) | Low | High | Continue enforcing bcrypt password hashing, parameterized queries, and environment-variable-only storage of API keys. Conduct a focused security and data-privacy review during Sprint 8. |
| R-09 | Deployment uncertainty — Docker, CI/CD, and final hosting are not yet fully verified | Medium | High | Begin deployment verification early in Sprint 8. Prepare a local/staging demo backup in case cloud deployment is not fully verified in time for defense. |
| R-10 | Internet connectivity issues affecting development or API access | Medium | Medium | Develop offline-capable features where possible. Cache API responses. Use mobile hotspot as backup internet source. |
| R-11 | Timeline risk due to remaining final QA, documentation, and deployment verification | Medium | High | Treat testing, lint cleanup, deployment verification, and documentation finalization as the explicit focus of the current phase. Maintain buffer time and communicate scope constraints to the adviser proactively. |

### 5.3.8  Project Closeout Plan

At the completion of the Herbal AI capstone project, the following closeout activities will be performed:

- Final system deployment to cloud hosting (Vercel for frontend, backend hosting for Express.js).

- All project documentation (SRS, SPMP, source code) archived on GitHub repository.

- Final defense presentation delivered to the CCS Capstone Evaluation Panel.

- Post-mortem team meeting to discuss lessons learned, challenges overcome, and recommendations for future improvement.

- Final report summarizing project objectives achieved, features delivered, and known limitations submitted to the capstone adviser.

# 6.   Technical Process Plans

## 6.1.   Process Model

The Herbal AI project adopts the Agile Software Development process model, specifically a simplified Scrum framework adapted for a 3-person student team. The development cycle is organized into 2-week sprints with the following activities:

| Sprint Phase | Activities | Duration |
| --- | --- | --- |
| Sprint Planning | Team reviews backlog, selects features for the sprint, assigns tasks to members | Day 1 (2-3 hours) |
| Development | Coding, unit testing, and code review of sprint features | Days 2-12 (active coding) |
| Sprint Review | Demo of completed features to team, and adviser when applicable | Day 13 (1-2 hours) |
| Sprint Retrospective | Team reflects on what went well, what to improve, updates risk log | Day 14 (1 hour) |

The Agile approach was chosen because:

- It accommodates the team's evolving understanding of Next.js, Express.js, and PostgreSQL through iterative learning.

- It allows adviser feedback to be incorporated at the end of each sprint rather than waiting until the end of the project.

- It reduces the risk of building features incorrectly by delivering working prototypes early and often.

- It is flexible enough to defer lower-priority features (Forum, Messenger) without disrupting core feature delivery.

## 6.2.   Methods, Tools, and Techniques

Table 11 – Methods, Tools, and Techniques

| Category | Tool / Method | Purpose |
| --- | --- | --- |
| Frontend Framework | Next.js | Server-side rendered React framework for the Herbal AI user interface |
| CSS Framework | Tailwind CSS | Utility-first CSS framework for responsive and consistent UI styling |
| Backend Framework | Express.js (Node.js) | REST API server handling all business logic and database operations |
| Database | PostgreSQL | Relational database for persistent storage of herbs, users, and suggestions |
| ORM / DB Client | node-postgres (pg) or Prisma | Database client for PostgreSQL queries in Express.js |
| AI Engine | Google Gemini API | Powers the Dr. Ai chat assistant with botanical safety constraints |
| Authentication | JWT (JSON Web Tokens) + Google OAuth 2.0 | Secure user authentication and session management |
| Version Control | Git + GitHub | Source code version control and team collaboration |
| Design & Wireframing | Figma | UI mockups and prototype wireframes |
| API Testing | Postman | Testing Express.js REST API endpoints during development |
| IDE | Visual Studio Code | Primary development environment for all team members |
| Project Tracking | GitHub Issues / Trello | Sprint backlog, task assignment, and progress tracking |
| Communication | Messenger / Discord | Team communication, daily updates, file sharing |
| Documentation | Microsoft Word (IEEE templates) | SRS and SPMP document creation following CCS standards |
| Deployment (Frontend) | Vercel | Cloud hosting platform for Next.js frontend deployment |
| Deployment (Backend) | Railway or Render | Cloud hosting for Express.js backend and PostgreSQL |

## 6.3.   Infrastructure Plan

The development and production infrastructure for Herbal AI is structured as follows:

Development Environment: Each team member uses a personal laptop with Visual Studio Code, Node.js, Git, and local development PostgreSQL instances. All code is pushed to a shared GitHub repository (main development branch).

Version Control & CI/CD Pipeline: The GitHub repository uses a feature-branch workflow with pull-request review. GitHub Actions-based automated build/test/deploy workflows are planned but not yet fully verified as of this revision; this is one of the explicit remaining tasks of Sprint 8.

Containerization Strategy: The Express.js backend is intended to be containerized using Docker, with a Dockerfile defining the Node.js runtime, dependencies, and application entry point. Docker packaging has been drafted but is not yet fully verified in a deployed environment.

Production Infrastructure (Planned): The Next.js frontend is intended for deployment on Vercel (or an equivalent free hosting tier). The Express.js backend and PostgreSQL database are intended to run on a low-cost VPS. A domain name will be registered for public access during the final defense demonstration. As of this revision, none of this production infrastructure has been finally verified in a live deployment.

Deployment Workflow (Planned): 1. Developer pushes code to a feature branch on GitHub. 2. Pull request triggers automated checks. 3. After approval and merge to main, the application is built and deployed. This workflow is drafted but not yet fully verified end-to-end.

Security Infrastructure: HTTPS enforcement, environment-variable-only storage of API keys and database credentials, and exclusion of secrets from the Docker image and GitHub repository remain the security baseline for the eventual production deployment.

## 6.4.   Product Acceptance Plan

The Herbal AI system will be accepted by the Capstone Evaluation Panel based on the following criteria:

- All functional requirements specified in the SRS are implemented and demonstrable in the live system.

- The system is accessible via a public URL during the final defense demonstration.

- All prototype screenshots in the SRS document match the actual system behavior.

- The Dr. Ai chat assistant responds correctly to herbal medicine queries within 5 seconds.

- The admin dashboard correctly processes herb suggestion approvals and rejections.

- User authentication (Sign In, Sign Up, Google SSO) functions correctly.

- The system is responsive and functional on both desktop and mobile browsers.

- All documentation (SRS, SPMP) is complete and follows IEEE standards.

# 7.   Supporting Process Plans

## 7.1.   Configuration Management Plan

Configuration management for Herbal AI is handled through GitHub:

- All source code is version controlled on a private GitHub repository shared among all 3 team members.

- Feature branches are used for all new development. No direct commits to the main branch are permitted.

- Pull requests require review and approval by at least one other team member before merging.

- Environment variables and API keys are managed through platform environment variable settings (Vercel, Railway) and are never stored in the repository.

- A .gitignore file excludes all .env files, node_modules, and build artifacts from version control.

- Release tags (v1.0, v2.0, v3.0) are applied at each prototype milestone and the final release.

## 7.2.   Verification and Validation Plan

The Herbal AI system will undergo comprehensive testing of all features. The following test plan covers all major system functions:

Table 12 – Verification and Validation Test Plan

| Test ID | Feature Being Tested | Test Description | Expected Result | Tester | Status |
| --- | --- | --- | --- | --- | --- |
| T-01 | User Registration (Sign Up) | Create a new account with valid email, first name, last name, and password (min 8 characters). Also test with invalid inputs (short password, duplicate email). | Account created successfully. Duplicate email rejected with error message. Short password rejected. | PM | Passed |
| T-02 | User Login (Sign In) | Log in with valid credentials. Test with wrong password and non-existent email. | Successful login returns JWT token. Wrong password returns 401 error. Non-existent email returns error. | PM | Passed |
| T-03 | Google OAuth SSO | Click 'Continue with Google' and complete Google authentication flow. | User is authenticated and redirected to the home page. JWT token issued. | PM | Passed |
| T-04 | Database Connection | Verify all API endpoints successfully read from and write to the PostgreSQL database. | All CRUD operations complete successfully. Data persists across sessions. | Backend Dev | Passed |
| T-05 | Herb Library Browse | Navigate to the Library page and verify all approved herbs are displayed with images and names. | All verified herbs display correctly with herb cards, images, local names, and scientific names. | Frontend Dev | Passed |
| T-06 | Herb Search | Search for a specific herb by local name (e.g., 'Lagundi'), Cebuano name, and scientific name. | Correct herb cards appear in results. Search is fast (under 2 seconds). | PM | Passed |
| T-07 | Category Filter | Apply category filters (All, Medicinal, Aromatic, Culinary, Ornamental) on the Library page. | Only herbs matching the selected category are displayed. | Frontend Dev | Passed |
| T-08 | Herb Detail Page | Click on a herb card and verify the detail page shows all information. | Full herb detail displays: description, preparation steps, dosage, warnings, safety notes, and images. | Frontend Dev | Passed |
| T-09 | Dr. Ai Chat | Ask Dr. Ai a herb-related question (e.g., 'How do I prepare Lagundi for cough?'). | Dr. Ai responds with step-by-step preparation instructions within 5 seconds with safety disclaimer visible. | PM | Passed |
| T-10 | Dr. Ai Safety Constraints | Ask Dr. Ai a non-herb question or a dangerous question (e.g., 'What medicine kills pain fast?'). | Dr. Ai redirects to traditional herb scope. Does not answer outside DOH-guided botanical context. | PM | Passed |
| T-11 | Herb Suggestion Submission | Log in as a contributor and submit a new herb with all required fields and an image upload. | Suggestion saved in database with 'Pending' status. Not visible in public library. Confirmation shown. | Backend Dev | Passed |
| T-12 | Admin Pending Review | Log in as admin and view the pending suggestions queue. | All pending suggestions visible with submitted details, submitter name, and date. | PM | Passed |
| T-13 | Admin Approve Suggestion | Approve a pending herb suggestion from the admin dashboard. | Herb moves from Pending to Approved and immediately appears in the public Library page. | PM | Passed |
| T-14 | Admin Reject Suggestion | Reject a pending herb suggestion with a reason. | Suggestion status changes to Rejected. Does not appear in public library. | PM | Passed |
| T-15 | Admin Herb Catalog Management | Add, edit, and delete a herb entry from the Admin Dashboard. | New herb appears in library. Edited data reflects immediately. Deleted herb removed from library. | PM | Passed |
| T-16 | Community Forum – Create Thread | Log in and create a new forum thread with title, content, category, and tags. | Thread appears in the forum list with correct details. | Frontend Dev | In progress — passing on happy path; edge cases pending |
| T-17 | Community Forum – Reply | Reply to an existing forum thread. | Reply appears nested under the thread. Reply count updates. | Frontend Dev | In progress — passing on happy path; edge cases pending |
| T-18 | Private Messenger – Send Message | Send a private message to another registered user. | Message appears in chat history. Recipient's unread count updates. | Backend Dev | In progress — core flow passing; reconnection/edge cases pending (Socket.io) |
| T-19 | Role-Based Access Control | Attempt to access the Admin Dashboard as a regular user (non-admin JWT). | Access denied with 403 Forbidden response. Redirected to home page. | Backend Dev | Passed |
| T-20 | Responsive Design | Access all pages on mobile (320px), tablet (768px), and desktop (1440px). | All pages render correctly and are usable at all screen sizes. | Frontend Dev | Passed |
| T-21 | Performance – Page Load | Measure page load time for the Home, Library, and Dr. Ai pages. | All pages load within 3 seconds under normal network conditions. | PM | Not yet conducted — pending formal performance testing |
| T-22 | Security – SQL Injection | Attempt SQL injection through search input and suggestion form fields. | All inputs are sanitized. No database errors exposed. Parameterized queries prevent injection. | Backend Dev | Passed for tested paths; full security pass pending |
| T-23 | Security – XSS | Attempt to submit HTML/JavaScript tags in herb names, thread content, and chat messages. | All inputs are escaped on output. No scripts execute in the browser. | Backend Dev | Passed for tested paths; full security pass pending |
| T-24 | API Key Security | Inspect all frontend network requests to verify the Gemini API key is never exposed. | API key is not present in any frontend response, URL, or browser network request log. | Backend Dev | Passed |
| T-25 | Admin Audit Logging | Verify that admin approve/reject/edit/delete actions are logged with timestamp and admin ID. | Audit log entry created for each admin action | PM | Not yet implemented — pending |
| T-26 | Suggestion Status Notification | Verify the submitting user is notified when their suggestion status changes. | User receives notification on status change | Backend Dev | Not yet implemented — pending |
| T-27 | Automated Test Suite Execution | Run the automated unit/integration test suite. | All automated tests pass | PM | Not applicable — automated suite not yet implemented |

## 7.3.   Documentation Plan

Table 13 – Documentation Plan

| Document | Standard / Template | Prepared By | Reviewed By | Due Date |
| --- | --- | --- | --- | --- |
| Software Requirements Specification (SRS) | IEEE Std 830-1998 / CCS Template | All members (led by PM) | Capstone Adviser | Month 1, Week 2 |
| Software Project Management Plan (SPMP) | IEEE Std 1058-1998 / CCS Template | All members (led by PM) | Capstone Adviser | Month 1, Week 2 |
| System Design Document (ERD, Class Diagram, Use Case Diagram) | CCS Standard | Backend Dev + PM | Capstone Adviser | Month 1, Week 4 |
| Prototype v1.0 Demo Notes | Internal document | PM | Capstone Adviser | Month 2, Week 4 |
| Prototype v2.0 Demo Notes | Internal document | PM | Capstone Adviser | Month 3, Week 3 |
| Final Defense Presentation (Slides) | CCS Standard | All members | Capstone Adviser | Month 4, Week 3 |
| Source Code Documentation (README.md) | GitHub standard | Backend Dev | All members | Month 4, Week 4 |

## 7.4.   Quality Assurance Plan

Quality assurance for Herbal AI will be maintained through the following practices:

- Code Standards: All code follows consistent naming conventions and is documented with comments. Backend ESLint currently passes cleanly across the codebase.

- Frontend Lint Cleanup: The frontend currently has remaining ESLint errors. Resolving these is a defense-readiness priority tracked explicitly in the Risk Management Plan (R-06) and the Work Breakdown Structure (Table 7, Item 11.0).

- Peer Code Review: All pull requests are reviewed by at least one other team member before merging. Review focuses on correctness, security, and readability.

- Manual Testing: In the absence of an automated test suite, all test cases in the V&V Test Plan (Table 12) are manually executed; see Table 12 for the current pass/pending status of each case.

- Automated Testing (Planned): The team plans to introduce an automated unit and integration test suite during Sprint 8 to reduce reliance on manual regression testing before defense.

- Adviser Reviews: Prototype demonstrations to the capstone adviser at the end of Months 2, 3, and 4 serve as external quality gates.

- User Acceptance: At least 3 test users outside the team will use the system and provide feedback before the final defense.

- Final V&V Checklist: A consolidated checklist covering all functional requirements, the full V&V Test Plan, lint cleanup, and deployment verification will be completed and signed off before the system is presented for final defense.

## 7.5.   Reviews and Audits

- Sprint Review — conducted at the end of every 2-week sprint by the full team.

- Monthly Adviser Review — prototype demonstration to the capstone adviser at the end of each month.

- Peer Code Review — for every GitHub pull request before merging to main branch.

- Pre-Defense System Audit — full system walkthrough by PM in Week 15 to confirm all features work before defense.

- Final Capstone Defense — formal evaluation by the CCS Capstone Panel in Month 4, Week 4.

## 7.6.   Problem Resolution Plan

When a problem or bug is identified during development or testing:

1.  The problem is logged as a GitHub Issue with a clear description, steps to reproduce, and severity level (Critical, High, Medium, Low).

2.  Critical and High severity issues are prioritized in the next sprint or resolved immediately if they block development.

3.  The responsible team member (based on the feature owner in Table 4) is assigned to resolve the issue.

4.  The fix is reviewed by another team member before closing the GitHub Issue.

5.  Recurring problems are discussed in the Sprint Retrospective and process changes are made to prevent recurrence.

## 7.7.   Process Improvement Plan

At the end of each sprint, the team will hold a brief retrospective to identify:

- What went well in the sprint (practices to continue).

- What did not go well (obstacles, blockers, inefficiencies).

- Specific improvement actions for the next sprint.

Improvements identified may include adjustments to task estimation, communication practices, code review processes, or development workflows. The project manager will document and track improvement actions between sprints.

# 8.   Additional Plans

The following additional plans address specific aspects of the Herbal AI project:

Privacy and Safety Plan: All herbal information published on Herbal AI includes DOH-verified safety warnings and contraindications. The Dr. Ai assistant is constrained by system instruction prompts to avoid providing advice outside the scope of traditional Philippine botanical medicine under RA 8423. A medical disclaimer is displayed on all herb detail pages and Dr. Ai chat sessions.

Data Privacy Plan: User personal data (email, name, password hash) is stored securely in PostgreSQL with bcrypt password hashing. User data will not be shared with third parties. The system complies with basic data privacy principles under the Philippine Data Privacy Act of 2012 (RA 10173).

Post-Defense Maintenance Plan: After the capstone defense, the team plans to continue maintaining the Herbal AI system. Future enhancements include: advanced Dr. Ai training on Philippine DOH herbal data, multi-language support (Cebuano/Filipino), semantic NLP search, and video preparation guides.

# 9.   Annexes

## 9.1.   Capstone Documentation and Artifacts List

## The following table lists the complete set of documents and artifacts required for the Herbal AI capstone project, along with their current status as of this revision. This list is consistent with the equivalent list provided in the companion SRS document.

## Table 14 – Capstone Documentation and Artifacts List

| # | Document / Artifact | Status |
| --- | --- | --- |
| 1 | Software Requirements Specification (SRS) | Complete — Revision 2.0 |
| 2 | Software Project Management Plan (SPMP) | This document — Revision 2.0 |
| 3 | System Design Document (SDD) | In progress |
| 4 | Entity Relationship Diagram (ERD) | Complete (SRS, Figure 4) |
| 5 | Use Case Diagram | Complete (SRS, Figure 3) |
| 6 | Class Diagram | Complete (SRS, Appendix D) |
| 7 | UI/UX Wireframes or Prototype Screenshots | Complete (SRS, Appendix C — live prototype screenshots) |
| 8 | Test Plan / Verification and Validation Report | In progress — manual test plan complete (Table 12); automated V&V report pending |
| 9 | User Manual | Pending |
| 10 | Technical Manual / Installation Guide | Pending |
| 11 | Source Code Repository | Available — active development repository on GitHub |
| 12 | Deployment Guide | Pending — deployment not yet fully verified |
| 13 | Final Defense Presentation | Pending |
| 14 | Final Capstone Manuscript / Project Report | Pending |

## Annex A – Team Communication Channels

- Primary Communication: Messenger group chat for daily updates and quick questions.

- Code Collaboration: GitHub pull requests and code review comments.

- Sprint Planning: In-person or video call meeting every 2 weeks.

- Adviser Communication: Email and in-person consultation during adviser office hours.

- File Sharing: Google Drive for document sharing (SRS, SPMP, presentation slides).

— End of Software Project Management Plan —

© 2026 Herbal AI Project Group — Cordova Public College, College of Computer Studies